## Checklist
ERPNext Opening Balances & Migration Reconciliation Checklist
The order to load opening balances into ERPNext — masters, opening stock, GL and party balances — and how to reconcile every figure back to your legacy system before go-live.
Getting opening balances right is what makes an ERPNext go-live trustworthy — if the trial balance, stock value and party outstandings don't match the legacy books on day one, nobody believes the reports that follow. This is a reference for the real ERPNext flow: load master data first, bring in opening stock through Stock Reconciliation, post opening GL and party balances against the Temporary Opening account, then reconcile every number back to your old system before you sign off. Work top to bottom — the sequence matters, because each stage depends on the one before it. Use it to brief your team and to sanity-check the work your implementation partner delivers.
Item | Why it matters
SEQUENCE & CUT-OVER
Fix a cut-over date and freeze the legacy books | Pick a clean period boundary (usually a month/year end). Opening balances are entered as of the day before go-live so day-one transactions post on top.
Produce the legacy trial balance, AR/AP ageing and stock valuation as at cut-over | These three reports are your reconciliation targets — every opening figure in ERPNext must trace back to them.
Load in dependency order | Masters first (Chart of Accounts, Items, Customers, Suppliers), then opening stock, then opening GL and party balances. Balances reference masters, so masters cannot come second.
Set the company's fiscal year and posting-date controls | Confirm the Fiscal Year exists and that period-closing / posting-date restrictions won't block back-dated opening entries.
MASTER DATA FIRST
Finalise the Chart of Accounts before any balance is posted | Every GL and party balance lands on an Account — restructuring the CoA after loading balances means redoing the entries.
Import Customers and Suppliers via Frappe Data Import | Use the Data Import tool with the doctype template; get GSTIN, state and default currency right so party ledgers and GST reports work from day one.
Import Items, Item Groups and UOMs | Opening stock in Stock Reconciliation is keyed on item_code, warehouse and stock UOM — these must exist first.
Set up Warehouses and Cost Centers | Opening stock posts to a Warehouse; opening GL and stock difference postings need the right Cost Center.
Enable 'Create Missing Party' only as a deliberate fallback | The Opening Invoice Creation Tool can auto-create parties, but importing clean Customer/Supplier masters first gives you control over grouping, GSTIN and currency.
OPENING STOCK (STOCK RECONCILIATION)
Use a Stock Reconciliation with Purpose = 'Opening Stock' | This is the correct doctype for bringing in opening quantities and valuation — not a Stock Entry — because it sets both qty and valuation rate as at the cut-over.
Set qty, valuation_rate and warehouse for every stocked item | Amount is qty x valuation rate; the total must reconcile to the legacy stock valuation. Use 'Edit Posting Date and Time' to date it at cut-over.
Handle serialised and batched items through the serial/batch bundle | For items tracked by serial no or batch no, provide serial_no / batch_no (or the Serial and Batch Bundle) so opening stock carries valid identifiers.
Set the Difference Account and Cost Center | The Stock Reconciliation books the opening stock value against its difference (expense) account — point it at your opening/temporary account, not a P&L expense.
Confirm perpetual-inventory GL matches the stock ledger | With perpetual inventory on, the opening stock value hitting the GL must equal the Stock Balance report total.
OPENING GL & TEMPORARY OPENING ACCOUNT
Confirm a 'Temporary Opening' account of account_type 'Temporary' exists | ERPNext posts the counter-entry of opening balances here; it must be of type Temporary. It should net to zero once every opening figure is loaded.
Post remaining GL opening balances via Journal Entry, voucher type 'Opening Entry' | Selecting voucher_type 'Opening Entry' sets is_opening = 'Yes' — the marker ERPNext uses to treat the JE as an opening balance rather than a period transaction.
Balance each opening Journal Entry against Temporary Opening | Debit/credit the real ledger accounts (cash, bank, fixed assets, loans, tax, equity) with the offset to Temporary Opening so the JE balances.
Do NOT re-enter balances already loaded elsewhere | Stock value comes from the Stock Reconciliation and AR/AP from opening invoices — exclude those control accounts from the GL Journal Entry to avoid double counting.
Date opening entries at the cut-over date | All opening entries share the as-at date so the first live day starts from a correct, dated position.
OPENING AR / AP PARTY BALANCES
Load customer outstandings with the Opening Invoice Creation Tool (Invoice Type = Sales) | It creates Sales Invoices with is_opening = 'Yes', one per outstanding amount, against the Temporary Opening account — reproducing the debtors ageing without re-billing goods.
Load supplier outstandings the same way (Invoice Type = Purchase) | Purchase Invoices flagged is_opening = 'Yes' post the creditors balance against Temporary Opening, party_type Supplier.
Enter one row per open document to preserve ageing and due dates | Bringing in each invoice's outstanding amount and due date keeps the ageing buckets accurate rather than a single lump per party.
Alternatively post party balances via an Opening Journal Entry with Party set | Where you only need net party balances, an 'Opening Entry' JE with party_type / party against Temporary Opening also works — but you lose invoice-level ageing.
Reconcile advances and unallocated payments deliberately | Customer advances / supplier prepayments should be carried as opening entries too, so party ledgers net correctly.
RECONCILE & SIGN-OFF
Trial Balance in ERPNext must equal the legacy trial balance | Run the Trial Balance as at the cut-over date and match it line by line to the legacy books.
Temporary Opening account nets to zero | Once stock, GL and party balances are all loaded, the Temporary Opening account should carry no balance — a non-zero figure means something is missing or doubled.
Accounts Receivable / Payable ageing matches the legacy ageing | Compare the AR and AP Summary reports (party-wise outstanding) to the old system, bucket by bucket.
Stock Balance value matches the legacy stock valuation | The Stock Balance total should equal both the legacy figure and the inventory control account in the GL.
Cross-check opening tax/GST balances against filed returns | Opening GST input/output and TDS balances should tie to the last filed GSTR / returns and the legacy ledger, so the first live filing period is clean.
Get written sign-off from finance before going live | Reconciled trial balance, AR/AP and stock, signed by the account owner, is the gate — no transactions until it's approved.
Acube Innovations · Official ERPNext Partner · acubeinnovations.com · +91 62358 66111